## Sheet1
Date | Effort (hours) | Details
2023-01-20 | 1 | Meeting (via Goole Meet)
2023-01-27 | 1 | Meeting (via Goole Meet)
2023-01-30 | 4 | Design IPF DSL
2023-01-31 | 3 | Design IPF DSL
2023-02-02 | 1 | Parser implementation
2023-02-03 | 5 | Parser implementation
2023-02-03 | 1 | Meeting (via Goole Meet)
2023-02-04 | 8 | Trying to implement parser using Superpower
2023-02-05 | 4 | Parser implementation
2023-02-06 | 6 | Parser implementation
2023-02-07 | 6 | Evaluator implementation
2023-02-08 | 8 | Evaluator implementation
2023-02-09 | 6 | Evaluator implementation
2023-02-10 | 5 | Evaluator implementation
2023-02-11 | 4 | Fixes for calculator
2023-02-12 | 8 | Refactoring the calculator
2023-02-13 | 6 | Web UI implementation
2023-02-14 | 6 | Web UI implementation
2023-02-15 | 4 | Web UI implementation
2023-02-18 | 6 | Project deployment on staging server
2023-02-18 | 3 | Fix calculator and UI bugs